## Sheet1
Sr. NO | Equipments | Quantity | Expected cost | Party Name | Purchase order date | Expected delivery date | Actual date of receving | Actual Cost | Tax | Tax amount | Total Amount | Advance | Remarks | Installment 2 | Remarks
1 | Raw Effluent Transfer Pump | 2 | 40000 | Before Delivary | 2019-06-21 | 2019-07-24 |  | 27400 | 0.12 | 3288 | 30688 | 0 |  | 30688
2 | Primary Clarifier Sludge Pump | 2 | 40000 | Before Delivary | 2019-06-21 | 2019-07-24 |  | 27400 | 0.12 | 3288 | 30688 | 0 |  | 30688
3 | Secondary Clarifier Sludge Pump | 2 | 40000 | Before Delivary | 2019-06-21 | 2019-07-24 |  | 27400 | 0.12 | 3288 | 30688 | 0 |  | 30688
4 | Air blower for aeration tank | 3 | 330000 | Before Delivary | 2019-06-26 | 2019-07-31 |  | 324000 | 0.18 | 58320 | 382320 | 0 |  | 382320
5 | Filter Feed Pump | 2 | 30000 | Before Delivary | 2019-06-21 | 2019-07-24 |  | 23208 | 0.12 | 2784.96 | 25992.96 | 0 |  | 25992.96
6 | Agitator with Gearbox and motor for dosing system | 3 | 90000 | ashirvad enginnering | yet to relese |  |  | 112500 | 0.18 | 20250 | 132750 | 0 |  | 132750
7 | Agitator withGearbox and motor for Neutralization/ Flocculation tank | 2 | 80000 | ashirvad enginnering | yet to release |  |  | 97500 | 0.18 | 17550 | 115050 | 0 |  | 115050
8 | Filter Press Feed Pump | 2 | 80000 | Before Delivary | 2019-06-21 | 2019-07-24 |  | 75650 | 0.12 | 9078 | 84728 | 0 |  | 84728
9 | Filter Press | 1 | 400000 | Before Delivary | 2019-06-24 | 2019-07-29 |  | 380000 | 0.18 | 68400 | 448400 | 0 |  | 448400
10 | Diffuser with assembly | 90 | 270000 | Before Delivary | 2019-06-26 | 2019-07-03 |  | 108000 | 0.18 | 19440 | 127440 | 0 |  | 127440
11 | Clarifier | 2 | 600000 | ashirvad enginnering | 12-07-2109 | - |  | 420000 | 0.18 | 75600 | 495600 | 105000 |  | 390600
12 | Pressure Sand Filter | 1 | [5 empty] | 75000 | 0.18 | 13500 | 88500 | 0 |  | 88500
13 | Activated Carbon Filter | 1 | [5 empty] | 93000 | 0.18 | 16740 | 109740 | 0 |  | 109740
14 | Control Panel | 1 | 125000 | ATP | yet to relese |  |  | 135000 | 0.18 | 24300 | 159300 | 0 |  | 159300
15 | MS Piping | 1 Lot | 130000 |  |  |  |  | 0 | 0.18 | 0 | 0 | 0 |  | 0
16 | Cabeling | 1 Lot | 70000 |  |  |  |  | 0 | 0.18 | 0 | 0 | 0 |  | 0
17 | Transportation |  | 50000 |  |  |  |  | 0 | 0.18 | 0 | 0 | 0 |  | 0
18 | Valves for MS Piping | 1 Lot | 30000 |  |  |  |  | 0 | 0.18 | 0 | 0 | 0 |  | 0
19 | Online pH meter | 1 | 10000 |  |  |  |  | 0 | 0.18 | 0 | 0 | 0 |  | 0
20 | UPVC Piping | 1 Lot | 50000 |  |  |  |  | 600000 |  | 0 | 600000
21 | Travelling and other expense |  | 50000 | [5 empty] | 0.18 | 0 | 0 | 0 |  | 0
22 | Erection Charges |  | 150000 | [6 empty] | 0 | 0
23 | Rotameter,pressure gauge | 1 Lot | 5000 | [5 empty] | 0.18 | 0 | 0 | 0 |  | 0
24 | Water meter | 1 | 5000 | [5 empty] | 0.18 | 0 | 0 | 0 |  | 0
25 | ABB Motor 2 hp for Filterpress | 1 | 8000 | shree rang enterprice | 2019-06-26 | 2019-07-31 |  | 7462 | 0.18 | 1343.16 | 8805.16 |  |  | 8805.16
26 | ABB Motor 25 hp 1440 RPM Foot mounted for Blower | 3 | 150000 | shree rang enterprice | 2019-06-26 | 2019-07-31 |  | 149808 | 0.18 | 26965.44 | 176773.44 | 0 |  | 176773.44
27 | MEE |  | 6200000 |  |  |  |  | 6215000 | 0.18 | 1118700 | 7333700 | 1900000 |  | 5433700
28 | RO |  | 4200000 |  |  |  | Total Profit | 3600000 | 0.18 | 648000 | 4248000 | 500000
|  |  | 13233000 |  |  |  | 2001672 | 12498328 | 0.18 | 2249699.04 | 14748027.04 | 2505000 |  | 12243027.04
|  |  | 14500000 |  |  |  |  | 14500000 |  | 0 | 14500000 | 0
|  |  | 1267000 | [6 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
0
0

## Sheet2
Total Project Cost | Tax | Tax Amount | Total Amount
14500000 | 18 | 2610000 | 17110000
Total Amount Received
500000 | 10 | 450000 | 50000 | 3060000 | 2505000 | 555000 | 5.55
2900000 | 10 | 2610000 | 290000
7000000 | 10 | 6300000 | 700000
4100000 | 10 | 3690000 | 410000
14500000 | 10 | 13050000 | 1450000