## Fuji Silvertech
Project Name | Fuji Silvertech |  |  |  | Contact Person Name | [5 empty] | Site Contact Person Name
Office Address |  |  |  |  | Designation | [5 empty] | Designation
Site Address |  |  |  |  | Contact Number | [5 empty] | Contact Number
|  | Document |  |  | 2019-04-05 | 2019-04-06 | 2019-04-07
Sales Work Order With Quotation
Operational Sheet |  | G:\My Drive\Maulik\Quotation 2018 - 2019\Fuji Silvertech\Operation Cost.xls
Budgetary Sheet |  | G:\My Drive\Maulik\Quotation 2018 - 2019\Fuji Silvertech\Cost calculation.xlsx
Proforma Invoice-1
Proforma Invoice-2
Drawing | Process Flow Diagram
| Civil G A Layout | N/A
| Section Drawing | N/A
| Fabrication drawing |  |  |  | DONE
| P & ID | ..\..\DRAWINGS\Fuji\P & ID.pdf |  |  | DONE
BOQ | Equipment & Material BOQ | ..\..\BOQ\Fuji BOQ.xlsx |  |  |  |  | DONE
|  | Purchase Order | Inspection Report | Delivery Challan | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29
Purchase | Fabrication, Agitator, Dosing System | bar: 2019-04-10 to 2019-04-25
Pump | bar: 2019-04-11 to 2019-04-18
Gearbox Motor | bar: 2019-04-12 to 2019-04-19
Dosing Pump | bar: 2019-04-12 to 2019-04-14
Control Panel | bar: 2019-04-10 to 2019-04-25
Sand Filter & Carbon Filter | bar: 2019-04-11 to 2019-04-24
HDPE Tank | bar: 2019-04-13 to 2019-04-20
Dispatch | bar: 2019-04-27
Transportation | bar: 2019-04-26
Tax Invoice
Sales Delivery Challan
E Way Bill
[5 empty] | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31
Installation | bar: 2019-05-20 to 2019-05-28
Commissioning | bar: 2019-05-29 to 2019-05-31

## FR Chem
Project Name | FR Chem |  |  |  | Contact Person Name | [5 empty] | Site Contact Person Name
Office Address |  |  |  |  | Designation | [5 empty] | Designation
Site Address |  |  |  |  | Contact Number | [5 empty] | Contact Number
|  | Document |  |  | 2019-03-25 | 2019-03-26 | 2019-03-27
Sales Work Order With Quotation |  | ..\QUOTATION\39_Quote_FR Chem_250 KLD ETP_Ahmedabad_Prit Patel.pdf
Operational Sheet
Budgetary Sheet |  | ..\..\BOQ\39_BOQ_FR Chem_250 KL ETP_Ahmedabad_Prit patel.xlsx
Proforma Invoice-1
Proforma Invoice-2
Drawing | Process Flow Diagram
| Civil G A Layout | ..\..\DRAWINGS\39_DRAWING_FR Chem_250 KLD ETP_Prit patel\01-FOUNDATION PLAN-R11 - BLOWER.pdf
Section Drawing
| Fabrication drawing | N/A
P & ID
BOQ | Equipment & Material BOQ | ..\..\BOQ\39_BOQ_FR Chem_250 KL ETP_Ahmedabad_Prit patel.xlsx
|  | Purchase Order | Inspection Report | Delivery Challan | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18
Purchase | Fabrication | N/A |  | Received
| Pump | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Pump_Lubi_Ahmedabad.pdf |  | Received
| Gearbox Motor | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Agitator with gear box and moor_Ashirwad engineering.pdf |  | Received
| Agitator |  |  | Received
| Dosing System |  |  | Received
| Control Panel | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Control Panel_Jignesh bhai.pdf |  | Received
| Diffuser | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Rehau Diffuser_SBS Envirocare_Delhi.pdf |  | Received
| Air Blower | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Blower_Kay Blowers_Ahmedabad.pdf |  | Received
| Filter Press | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Filter Press_Jayco Filter Press_Ahmedabad.pdf |  | Received
| Tube Settling Media | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Tube Settling Media_Hariyana.pdf |  | Received
| GI Pipe | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_GI pipe_kantilal & brothers.pdf |  | Received
| Motor | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_Motor_Shree Rang.pdf |  | Received
| Sand Filter & Carbon Filter | ..\..\PURCHASE ORDER\39_PO_FR Chem_250 KL ETP_Ahmedabad_Prit patel\39_PO_PSF & ACF_Techwell.pdf |  | Received
Dispatch
Transportation
Tax Invoice
Sales Delivery Challan
E Way Bill
[5 empty] | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09
Installation | bar: 2019-03-13 to 2019-03-23
Commissioning | bar: 2019-03-25 to 2019-04-09

## Patel Texcot
Project Name | Patel Texcot |  |  |  | Contact Person Name | [5 empty] | Site Contact Person Name
Office Address |  |  |  |  | Designation | [5 empty] | Designation
Site Address |  |  |  |  | Contact Number | [5 empty] | Contact Number
|  | Document |  |  | 2019-03-25 | 2019-03-26 | 2019-03-27
Sales Work Order With Quotation
Operational Sheet
Budgetary Sheet
Proforma Invoice-1
Proforma Invoice-2
Drawing | Process Flow Diagram
| Civil G A Layout | ..\..\DRAWINGS\38_DRAWING_Patel Medicot_250 KL ETP_Rajkot_\Final Civil Drg..pdf
Section Drawing
| Fabrication drawing | N/A
| P & ID | ..\..\DRAWINGS\38_DRAWING_Patel Medicot_250 KL ETP_Rajkot_\005-P&ID-250KLD-ZLD-R1.pdf
BOQ | Equipment & Material BOQ
|  | Purchase Order | Inspection Report | Delivery Challan | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17
Purchase | Fabrication | N/A
Pump
Gearbox Motor | bar: 2019-06-18 to 2019-07-03
Clarifier | bar: 2019-06-18 to 2019-07-11
Agitator | bar: 2019-06-18 to 2019-07-03
Dosing System | bar: 2019-06-18 to 2019-07-03
Control Panel | bar: 2019-06-19 to 2019-07-10
Diffuser | bar: 2019-06-19 to 2019-07-04
Air Blower | bar: 2019-06-20 to 2019-07-10
Filter Press | bar: 2019-06-21 to 2019-07-11
Motor | bar: 2019-06-21 to 2019-07-01
Sand Filter & Carbon Filter | bar: 2019-06-22 to 2019-07-10
Dispatch
Transportation
Tax Invoice
Sales Delivery Challan
E Way Bill
[5 empty] | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30
Installation | bar: 2019-04-28 to 2019-05-13
Commissioning | bar: 2019-05-15 to 2019-05-30

## Aico Foods
Project Name | Aico Foods |  |  |  | Contact Person Name | [5 empty] | Site Contact Person Name
Office Address | 44 Hirabhai Market, Diwan Ballubhai Road, Kankariya, Ahmedabad 380 022 |  |  |  | Designation | [5 empty] | Designation
Site Address | Survey No. 661, Moje: Gangad , Taluka: Bavla, Dist: Ahmedabad |  |  |  | Contact Number | [5 empty] | Contact Number
|  | Document |  |  | 2019-05-03 | 2019-05-04 | 2019-05-05
Sales Work Order With Quotation |  | ..\Sales Work Order\17_PO_Aico Food_100 KLD ETP_Amit Chopra.pdf
Operational Sheet
Budgetary Sheet |  | ..\..\BOQ\17_BOQ_Aico Food_100 KLD_Amit chopra.xlsx
Proforma Invoice-1
Proforma Invoice-2
Drawing | Process Flow Diagram | ..\..\DRAWINGS\17_DRAWING_Aico foods_100 KLD_Amit chopra\PFD 100 KLD ETP Model (1).pdf
| Civil G A Layout | ..\..\DRAWINGS\17_DRAWING_Aico foods_100 KLD_Amit chopra\17_Autocad DRAWING_Aeco foods_Amit chopra\Etp final drg.dwg
| Section Drawing | ..\..\DRAWINGS\17_DRAWING_Aico foods_100 KLD_Amit chopra\17_Autocad DRAWING_Aeco foods_Amit chopra\Etp final drg.dwg
| Fabrication drawing | N/A
GA Layout
| P & ID | ..\..\DRAWINGS\17_DRAWING_Aico foods_100 KLD_Amit chopra\P&ID 100 KLD ETP Model (1).pdf
BOQ | Equipment & Material BOQ | ..\..\BOQ\17_BOQ_Aico Food_100 KLD_Amit chopra.xlsx
|  | Purchase Order | Inspection Report | Delivery Challan | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03
Purchase | Pump | bar: 2019-05-06 to 2019-05-31
Gearbox Motor | bar: 2019-05-07 to 2019-05-14
Agitator with skid | bar: 2019-05-08 to 2019-05-23
Dosing System | bar: 2019-05-08 to 2019-05-23
Air Blower | bar: 2019-05-07 to 2019-05-28
Diffuser | bar: 2019-05-08 to 2019-05-15
Filter Press | bar: 2019-05-09 to 2019-05-29
Motor for Blower and Filter press | bar: 2019-05-08 to 2019-05-15
Control Panel | bar: 2019-05-08 to 2019-05-27
Water Meter | bar: 2019-05-09 to 2019-05-14
Sand Filter & Carbon Filter | bar: 2019-05-07 to 2019-05-26
Dispatch | bar: 2019-06-02 to 2019-06-03
Transportation | bar: 2019-05-30 to 2019-06-01
Tax Invoice
Sales Delivery Challan
E Way Bill | bar: 2019-06-02 to 2019-06-03
[5 empty] | 2019-06-15 | 2019-06-16 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09
Installation | bar: 2019-06-15 to 2019-06-22
Commissioning | bar: 2019-06-24 to 2019-07-09

## Ratnakar Estate
Project Name |  |  |  |  | Contact Person Name | [5 empty] | Site Contact Person Name
Office Address |  |  |  |  | Designation | [5 empty] | Designation
Site Address |  |  |  |  | Contact Number | [5 empty] | Contact Number
|  | Document |  |  | 2019-03-25 | 2019-03-26 | 2019-03-27
Sales Work Order With Quotation |  | ..\Sales Work Order\17_PO_Aico Food_100 KLD ETP_Amit Chopra.pdf
Operational Sheet
Budgetary Sheet
Proforma Invoice-1
Proforma Invoice-2
Drawing | Process Flow Diagram
| Civil G A Layout | Done
| Section Drawing | Done
| Fabrication drawing | N/A
P & ID
BOQ | Equipment & Material BOQ | ..\..\BOQ\17_BOQ_Aico Food_100 KLD_Amit chopra.xlsx
|  | Purchase Order | Inspection Report | Delivery Challan | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25
Purchase | Pump | bar: 2019-03-28 to 2019-04-10
Air Blower | bar: 2019-03-29 to 2019-04-13
Diffuser | bar: 2019-03-30 to 2019-04-06
Control Panel | bar: 2019-03-31 to 2019-04-15
Water Meter | bar: 2019-03-31 to 2019-04-05
Sand Filter & Carbon Filter | bar: 2019-04-01 to 2019-04-16
Dispatch | bar: 2019-04-20
Transportation | bar: 2019-04-17 to 2019-04-19
Tax Invoice
Sales Delivery Challan | bar: 2019-04-19
E Way Bill
[5 empty] | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24
Installation | bar: 2019-03-13 to 2019-03-18
Commissioning | bar: 2019-03-19 to 2019-03-24

## Moly Metals
Project Name | Moly Metals |  |  |  | Contact Person Name | [5 empty] | Site Contact Person Name
Office Address | 202, Aditya Bldg., Mithakhali Six Road, Ellis Bridge, Ahmedabad - 380 006, Gujarat, India |  |  |  | Designation | [5 empty] | Designation
Site Address | PLOT NO. 317, PHASE 1 GIDC CHHATRAL, GUJARAT 382729 |  |  |  | Contact Number | [5 empty] | Contact Number
|  | Document |  |  | 2019-04-30
Sales Work Order With Quotation |  | ..\Sales Work Order\48_PO_Moly Metal LLP_200 Liter Evaporator with Sand & Carbon Filter_Ahmedabad.pdf
Operational Sheet
Budgetary Sheet |  | ..\..\..\Maulik\Quotation 2018 - 2019\Moly Metals\Cost calculation.xlsx
Proforma Invoice-1
Proforma Invoice-2
Drawing | Process Flow Diagram | N/A
| Civil G A Layout | N/A
| Section Drawing | N/A
Fabrication drawing
P & ID
BOQ | Equipment & Material BOQ | ..\..\BOQ\Moly Metal BOQ.xlsx
|  | Purchase Order | Inspection Report | Delivery Challan | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29
Purchase | Filter Feed Pump | bar: 2019-05-01 to 2019-05-03
Sand Filter and Carbon Filter | bar: 2019-05-02 to 2019-05-11
Evaporator | bar: 2019-05-04 to 2019-05-14
Dispatch | bar: 2019-05-16
Transportation | bar: 2019-05-15
Tax Invoice
Sales Delivery Challan
E Way Bill
[5 empty] | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24
Installation | bar: 2019-03-13 to 2019-03-18
Commissioning | bar: 2019-03-19 to 2019-03-24