## Sheet1
Sr. NO | Equipments | Quantity | Expected cost | Party Name | Purchase order date | Expected delivery date | Actual date of receving | Actual Cost | Tax | Tax amount | Total Amount | Advance | Remarks | Installment 2 | Remarks
1 | Raw Effluent Transfer Pump | 2 | 20000 | Shree Krishna Enterprise | 2018-11-29 | 2018-12-05 |  | 18606 | 12% | 2232.72 | 20838.72 | 0 | Payment After Delivery within 15 days | 20838.72
2 | PST Sludge Pump | 2 | 20000 |  |  |  |  | 18606 | 12% | 2232.72 | 20838.72 |  |  | 20838.72
3 | SST Sludge Pump | 2 | 20000 |  |  |  |  | 18606 | 12% | 2232.72 | 20838.72 | 0 |  | 20838.72
4 | Filter Feed Pump | 2 | 20000 |  |  |  |  | 17346 | 12% | 2081.52 | 19427.52 |  |  | 19427.52
5 | Air blower for aeration tank | 2 | 150000 | TMVT | 2018-11-28 | 2018-12-06 |  | 120000 | 18% | 21600 | 141600 | 0 | PDC of15 days after delivery | 141600
6 | Motor for Blower BBL 7.5 Hp 1440 RPM Foot mounted | 2 | 30000 | Shree Rang Enterprise | 2018-11-28 | 2018-12-04 |  | 29000 | 18% | 5220 | 34220 | 0 | Payment After Delivery within 15 days | 34220
7 | Dosing System | 2 | 50000 | Techwell | 2018-12-03 | 2018-12-10 |  | 23000 | 18% | 4140 | 27140 | 0 | Payment After Delivery within 15 days | 27140
8 | Agitator | 2 | 70000 | Ashirwad Engineers | 0 | 2018-12-15 |  | 50000 | 18% | 9000 | 59000 | 0 | Payment After Delivery within 15 days | 59000
9 | Diffuser | 26 | 50000 | Techwell | 2018-12-03 | 2018-12-10 |  | 25350 | 18% | 4563 | 29913 | 0 | Payment After Delivery within 15 days | 29913
11 | Pressure Sand Filter & Activated Carbon Filter | 1 | 65000 | OK Water System | 2018-11-29 | 2018-12-05 |  | 65000 | 18% | 11700 | 76700 | 0 | Payment After Delivery within 15 days | 76700
12 | Control Panel | 1 | 50000 | ATP Power House | 2018-12-08 | 2018-12-15 |  | 60000 | 18% | 10800 | 70800 | 0 | Payment After Delivery within 15 days | 70800 | Approximate Budget
13 | Piping |  | 150000 |  |  |  |  | 120000 | 18% | 21600 | 141600 | 50000 |  | 91600 | Approximate Budget
14 | Cabeling |  | 10000 |  |  |  |  | 10000 | 18% | 1800 | 11800 | 0 |  | 11800
15 | Valves for MS Piping |  | 10000 |  |  |  |  | 10000 | 18% | 1800 | 11800 | 11800 |  | 0
16 | [8 empty] | 18% | 0 | 0 | 0 |  | 0
17 | Travelling and other expense |  | 50000 | [5 empty] | 18% | 0 | 0 | 0 |  | 0
18 | Rotameter,pressure gauge |  | 5000 |  |  |  |  | 5000 | 18% | 900 | 5900 | 0 |  | 5900
19 | Water meter |  | 5000 |  |  |  |  | 5000 | 18% | 900 | 5900 | 0 |  | 5900
|  |  | 775000 |  |  |  |  | 595514 | 18% | 107192.52 | 702706.52 | 61800 |  | 640906.52

## Sheet2
| 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21
Raw Effluent Transfer Pump | bar: 2018-12-05 to 2018-12-06
SST Sludge Pump | bar: 2018-12-05 to 2018-12-06
Filter Feed Pump | bar: 2018-12-05 to 2018-12-06
Air blower for aeration tank
Motor for Blower BBL 7.5 Hp 1440 RPM Foot mounted
Dosing System
Agitator
Diffuser
Pressure Sand Filter & Activated Carbon Filter
Control Panel
Piping
Cabeling
Valves for MS Piping
Travelling and other expense
Rotameter,pressure gauge
Water meter

## Sheet3
Delivery challan
Date: 13-03-2019
Delivery Address: M/S GALLOPS INDUSTRIAL PARK-2,SARKHEJ-BAVALA HIGHWAY,VASANA-CHACHRVADI AHMEDABAD-382213 |  |  | Challan No. 15
Contact person
Sr. No | Equipments | size | NOS
1 | Rubber Gasket 1 1/2" |  | 6
2 | Rubber Gasket 2" |  | 2
3 | Nut-Bolt 2 1/2 x 1/2 |  | 50
4 | Khilla 1 1/2" |  | 50
5 | Teflon Tape |  | 20
6 | Foot Valve 1 1/2 |  | 2
7 | MS Flange 1 1/4" |  | 2
8 | MS Elbow 1 1/4" |  | 8
9 | MS Pipe 1 1/4" |  | 20 feet
10 | Ms Refuser 1 1/4" x 1" |  | 1
11 | MS Coupling 1" |  | 1
12 | Flange 2" |  | 3
13 | FTA 1" |  | 15
14 | MTA 1" |  | 15
15 | Flange 1 1/2" |  | 4
16 | Bushing 2" x 1 1/2" |  | 6
17 | Tee 1" |  | 4
18 | Ball Valve 1" |  | 8
19 | Ball Valve 1 1/2" |  | 10
20 | Union 1" |  | 6
21 | Union 1 1/2" |  | 10
22 | Tee 1 1/2" |  | 3
23 | Pipe 1 1/2" |  | 30 Meter
24 | Pipe 1" |  | 24 Meter
25 | Elbow 1" |  | 30 Nos
26 | Elbow 1 1/2" |  | 35 Nos
27 | Solution |  | 1 Ltr
2019-03-13 | Checked By | For, ENVIRON
Received By,